## Bug 445
BUG ID : 445
Bug Description:
When Clicking on Approve in Title Workflow Page , the page shows Error - Delivery Role (Title Registration)
Pre-Requisites:
Complete Title Registration Steps in Teller Role
Complete Title Registration Steps in Officer Role
Complete Title Registration Steps in Payment Role
STEPS TO REPRODUCE:
Click on Dashboard
Search the Party by entering valid License Plate no in Search box
Select Claim option under Action Column
Click on Approve
Click on Checkbox for Title Registration
Click on Checkbox for Delivery Role
Click on Checkbox for Verify Delivery Documents
Select All and Click on Approve
The Page is showing Error
Expected Result:
The Title Registration will be done and added to Transactions List
Actual Result:
The Page is showing Error
Screenshot : http://teams.piitech.com/issues/445
Tester Name : Muhammed Azar
Version - RTA 2.0

## Bug 66
BUG ID : 66
Bug Description:
When Clicking on Select Vehicle in Vehicle Transfer Page , the Search results are not displayed - Teller Role
STEPS TO REPRODUCE:
Login with Teller Role Credentials
Click on Transfer
Click on Select Vehicle in Vehicle Transfer Page
Click on Search in Vehicle List Page
Enter License Plate no
The Search results are not displayed
Expected Result:
The Vehicle should be listed in Search Results
Actual Result:
The Search results are not displayed
Screenshot : http://teams.piitech.com/issues/66
Tester Name : Muhammed Azar
Version - RTA 2.0

## Bug 62
BUG ID : 62
Bug Description:
When Clicking on Assign Smart Tag in Home Page , the page is showing Smart Tag Not Found- Teller Role
STEPS TO REPRODUCE:
Login with Teller Role Credentials
Click on Assign Smart Tag
The Page is showing Smart Tag Not Found
Expected Result:
The Smart Tag Page should open
Actual Result:
The Page is showing Smart Tag Not Found
Screenshot : http://teams.piitech.com/issues/62
Tester Name : Muhammed Azar
Version - RTA 2.0

## Bug 61
BUG ID : 61
Bug Description:
When Clicking on Tax Collection in Home Page , the page is showing Error- Teller Role
STEPS TO REPRODUCE:
Login with Teller Role Credentials
Click on Assign Smart Tag
The Page is showing Smart Tag Not Found
Expected Result:
The Smart Tag Page should open
Actual Result:
The Page is showing Smart Tag Not Found
Screenshot : http://teams.piitech.com/issues/62
Tester Name : Muhammed Azar
Version - RTA 2.0